## Sheet1
Plan vs Achievement
Date: | 26-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 84080 | 2343382 | 1997231 | [6 empty] | 83442 |  |  | 7.11 | 7.06 | 10 | 10.36 | 68% | 71.98% |  |  | 26 | 22
JAL3 | 9695 | 285887 | 242950 | [6 empty] | 10058 |  |  | 5.96 | 6.06 | 10 | 8.93 | 68% | 75.84% |  |  | 26 | 22
JFL | 59753 | 1652169 | 1231687 | [6 empty] | 48184 |  |  | 6.07 | 5.33 | 10.5 | 9.26 | 72% | 77.42% |  |  | 26 | 22
JKL | 55475 | 1755763 | 1372847 | [6 empty] | 68688 |  |  | 10.32 | 9.76 | 9 | 10.04 | 60% | 57.85% |  |  | 26 | 22
MFL | 76120 | 2319422 | 1781971 | [6 empty] | 85449 |  |  | 7.5 | 7.19 | 10 | 9.53 | 64% | 67.71% |  |  | 26 | 22
FFL2 | 72637 | 2196792 | 1906905 | [6 empty] | 79212 |  |  | 7.88 | 7.87 | 10 | 12.52 | 68% | 62.61% |  |  | 26 | 22
JKL-U2 | 102129 | 3634362 | 2305385 | [6 empty] | 113749 |  |  | 8.67 | 8.01 | 10 | 8.78 | 65% | 66.65% |  |  | 26 | 22
GTAL | 13222 | 335974 | 125352 | [6 empty] | 21883 |  |  | 6.61 | 5.59 | 8 | 8.07 | 63% | 6.85% |  |  | 26 | 22
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 110100 | 3013766 | 2722784 | [6 empty] | 100015 |  |  | 3.89 | 4.12 | 8.82 | 9.81 | 74% | 76.22% |  |  | 26 | 22
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-