## Sheet1
Plan vs Achievement
Date: | 06-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 76450 | 2203539 | 428335 | [6 empty] | 78044 |  |  | 7.6 | 8.56 | 10 | 10.17 | 72% | 71.04% |  |  | 26 | 6
JAL3 | 14195 | 313636 | 83380 | [6 empty] | 12450 |  |  | 6.47 | 6.11 | 10 | 11.64 | 72% | 74.88% |  |  | 26 | 6
JFL | 41080 | 1498277 | 260295 | [6 empty] | 40702 |  |  | 6.49 | 5.79 | 10 | 8.82 | 73% | 69.7% |  |  | 26 | 6
JKL | 54181 | 2014480 | 337097 | [6 empty] | 60870 |  |  | 9.27 | 8.97 | 10 | 8.42 | 65% | 55.83% |  |  | 26 | 6
MFL | 65500 | 2332178 | 410418 | [6 empty] | 75168 |  |  | 7.82 | 7.72 | 10 | 9.18 | 72% | 65.35% |  |  | 26 | 6
FFL2 | 89955 | 2597126 | 482680 | [6 empty] | 90447 |  |  | 7.34 | 8.42 | 10 | 12.17 | 73% | 66.66% |  |  | 26 | 6
JKL-U2 | 93370 | 3823698 | 588683 | [6 empty] | 102155 |  |  | 8.14 | 9.09 | 10 | 9.25 | 72% | 66.49% |  |  | 26 | 6
GTAL | 2375 | 36509 | 42231 | [6 empty] | 6046 |  |  | 7.67 | 6.92 | 10 | 8.04 | 63% | 11.58% |  |  | 26 | 6
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 131120 | 3461205 | 800250 | [6 empty] | 124578 |  |  | 4.22 | 3.88 | 10 | 10.04 | 80% | 77.35% |  |  | 26 | 6
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-