## Sheet1
Plan vs Achievement
Date: | 16-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 73280 | 2203539 | 1026426 | [6 empty] | 77040 |  |  | 7.6 | 8.25 | 10 | 10.25 | 72% | 70.44% |  |  | 26 | 14
JAL3 | 8960 | 313636 | 163065 | [6 empty] | 9694 |  |  | 6.47 | 6.21 | 10 | 10.03 | 72% | 73.23% |  |  | 26 | 14
JFL | 38438 | 1498277 | 561794 | [6 empty] | 38497 |  |  | 6.49 | 5.99 | 10 | 8.72 | 73% | 69.1% |  |  | 26 | 14
JKL | 45632 | 2014480 | 731861 | [6 empty] | 52397 |  |  | 9.27 | 9.52 | 10 | 8.45 | 65% | 56.62% |  |  | 26 | 14
MFL | 73687 | 2332178 | 975683 | [6 empty] | 75349 |  |  | 7.82 | 7.69 | 10 | 9.16 | 72% | 66.99% |  |  | 26 | 14
FFL2 | 95940 | 2597126 | 1262585 | [6 empty] | 105940 |  |  | 7.34 | 7.63 | 10 | 12.25 | 73% | 67.31% |  |  | 26 | 14
JKL-U2 | 101817 | 3823698 | 1398158 | [6 empty] | 110106 |  |  | 8.14 | 9 | 10 | 9.4 | 72% | 66.47% |  |  | 26 | 14
GTAL | 10592 | 48509 | 64587 | [6 empty] | 0 |  |  | 7.67 | 5.04 | 10 | 7.96 | 63% | 6.08% |  |  | 26 | 14
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 132530 | 3461205 | 1887589 | [6 empty] | 135422 |  |  | 4.22 | 3.81 | 10 | 10.21 | 80% | 76.09% |  |  | 26 | 14
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-