## Sheet1
Plan vs Achievement
Date: | 18-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 80092 | 2203539 | 1184205 | [6 empty] | 82352 |  |  | 7.6 | 8.2 | 10 | 10.32 | 72% | 70.29% |  |  | 26 | 16
JAL3 | 12940 | 313636 | 187693 | [6 empty] | 12989 |  |  | 6.47 | 6.29 | 10 | 10.33 | 72% | 72.95% |  |  | 26 | 16
JFL | 41212 | 1498277 | 643611 | [6 empty] | 41471 |  |  | 6.49 | 6.08 | 10 | 8.88 | 73% | 68.6% |  |  | 26 | 16
JKL | 46204 | 2014480 | 824844 | [6 empty] | 56770 |  |  | 9.27 | 9.67 | 10 | 8.44 | 65% | 56.87% |  |  | 26 | 16
MFL | 76479 | 2332178 | 1126028 | [6 empty] | 81368 |  |  | 7.82 | 7.64 | 10 | 9.17 | 72% | 67.33% |  |  | 26 | 16
FFL2 | 94970 | 2597126 | 1447647 | [6 empty] | 101240 |  |  | 7.34 | 7.55 | 10 | 12.12 | 73% | 67.57% |  |  | 26 | 16
JKL-U2 | 106618 | 3823698 | 1609942 | [6 empty] | 117767 |  |  | 8.14 | 8.91 | 10 | 9.39 | 72% | 66.37% |  |  | 26 | 16
GTAL | 12385 | 48509 | 81896 | [6 empty] | 26364 |  |  | 7.67 | 5.85 | 10 | 7.97 | 63% | 7.66% |  |  | 26 | 16
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 123257 | 3461205 | 2141956 | [6 empty] | 113388 |  |  | 4.22 | 3.79 | 10 | 10.16 | 80% | 75.71% |  |  | 26 | 16
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-