## Sheet1
Plan vs Achievement
Date: | 19-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 79021 | 2203539 | 1263226 | [6 empty] | 80334 |  |  | 7.6 | 8.19 | 10 | 10.35 | 72% | 70.25% |  |  | 26 | 17
JAL3 | 11690 | 313636 | 199383 | [6 empty] | 12295 |  |  | 6.47 | 6.37 | 10 | 10.48 | 72% | 72.7% |  |  | 26 | 17
JFL | 41312 | 1498277 | 684923 | [6 empty] | 43556 |  |  | 6.49 | 6.1 | 10 | 8.94 | 73% | 68.27% |  |  | 26 | 17
JKL | 49573 | 2014480 | 874417 | [6 empty] | 56657 |  |  | 9.27 | 9.73 | 10 | 8.48 | 65% | 56.92% |  |  | 26 | 17
MFL | 77983 | 2332178 | 1204011 | [6 empty] | 83006 |  |  | 7.82 | 7.61 | 10 | 9.18 | 72% | 67.43% |  |  | 26 | 17
FFL2 | 93716 | 2597126 | 1541363 | [6 empty] | 100628 |  |  | 7.34 | 7.53 | 10 | 12.08 | 73% | 67.69% |  |  | 26 | 17
JKL-U2 | 114703 | 3823698 | 1725205 | [6 empty] | 116113 |  |  | 8.14 | 8.84 | 10 | 9.39 | 72% | 66.42% |  |  | 26 | 17
GTAL | 14737 | 48509 | 96633 | [6 empty] | 27095 |  |  | 7.67 | 5.78 | 10 | 7.97 | 63% | 8.37% |  |  | 26 | 17
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 115869 | 3461205 | 2257825 | [6 empty] | 118524 |  |  | 4.22 | 3.8 | 10 | 10.11 | 80% | 75.52% |  |  | 26 | 17
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-