## Sheet1
Plan vs Achievement
Date: | 22-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 83457 | 2203539 | 1432443 | [6 empty] | 86472 |  |  | 7.6 | 8.15 | 10 | 10.42 | 72% | 70.28% |  |  | 26 | 19
JAL3 | 10220 | 313636 | 223131 | [6 empty] | 10875 |  |  | 6.47 | 6.49 | 10 | 10.54 | 72% | 72.61% |  |  | 26 | 19
JFL | 41225 | 1498277 | 768561 | [6 empty] | 41520 |  |  | 6.49 | 6.19 | 10 | 9.01 | 73% | 67.74% |  |  | 26 | 19
JKL | 67450 | 2014480 | 995805 | [6 empty] | 76600 |  |  | 9.27 | 9.76 | 10 | 8.64 | 65% | 57.29% |  |  | 26 | 19
MFL | 77760 | 2332178 | 1356304 | [6 empty] | 81514 |  |  | 7.82 | 7.57 | 10 | 9.19 | 72% | 67.67% |  |  | 26 | 19
FFL2 | 100738 | 2597126 | 1739446 | [6 empty] | 99493 |  |  | 7.34 | 7.45 | 10 | 12.07 | 73% | 67.86% |  |  | 26 | 19
JKL-U2 | 123472 | 3823698 | 1974749 | [6 empty] | 130712 |  |  | 8.14 | 8.71 | 10 | 9.45 | 72% | 66.57% |  |  | 26 | 19
GTAL | 18676 | 48509 | 134493 | [6 empty] | 27522 |  |  | 7.67 | 5.7 | 10 | 7.98 | 63% | 10.18% |  |  | 26 | 19
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 116156 | 3461205 | 2495638 | [6 empty] | 124622 |  |  | 4.22 | 3.8 | 10 | 10.08 | 80% | 74.96% |  |  | 26 | 19
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-