## Sheet1
Plan vs Achievement
Date: | 02-Dec-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 94734 | 2746419 | 191001 | [6 empty] | 95389 |  |  | 7.05 | 6.65 | 10 | 10.11 | 70% | 73.85% |  |  | 26 | 2
JAL3 | 13900 | 350940 | 26815 | [6 empty] | 11987 |  |  | 7.05 | 6.39 | 10 | 12.35 | 70% | 73.59% |  |  | 26 | 2
JFL | 40851 | 1530868 | 82440 | [6 empty] | 39357 |  |  | 6.78 | 7.71 | 11 | 11.27 | 74% | 66.1% |  |  | 26 | 2
JKL | 71037 | 2273631 | 143593 | [6 empty] | 82017 |  |  | 8.41 | 8.23 | 10 | 9.14 | 63% | 59.52% |  |  | 26 | 2
MFL | 70454 | 2343006 | 142277 | [6 empty] | 76534 |  |  | 7.38 | 7.09 | 10 | 8.96 | 71% | 66.16% |  |  | 26 | 2
FFL2 | 112261 | 2907274 | 219012 | [6 empty] | 114723 |  |  | 6.53 | 5.98 | 10 | 10.53 | 68% | 75.01% |  |  | 26 | 2
JKL-U2 | 127014 | 3971692 | 251423 | [6 empty] | 134112 |  |  | 7.9 | 7.41 | 10 | 9.45 | 68% | 66.91% |  |  | 26 | 2
GTAL | 41537 | 0 | 86346 | [6 empty] | 64769 |  |  | 0 | 4.63 | 10 | 10.44 | 63% | 43.67% |  |  | 26 | 2
GMT TOTAL: | [12 empty] | 7.38 |  | 10 |  | 68.63% |  |  |  | 26
LINGERIE | 137040 | 3336726 | 255170 | [6 empty] | 123461 |  |  | 4.19 | 3.77 | 10.08 | 10.05 | 79% | 72.63% |  |  | 26 | 2
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-