## Sheet1
Plan vs Achievement
Date: | 28-Dec-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 89114 | 2724653 | 2234376 | 490277 | 2421913.7778 | 187537.7778 | 144847.75 | 1021176.6375 | 622015.72 | 87102 | 91.34% | 14484.775 | 7.05 | 6.98 | 10 | 10.84 | 70% | 72.25% | 15595944.48 | 17074492.1333 | 27 | 24 | 3
JAL3 | 10080 | 350940 | 317305 | 33635 | 311946.6667 | -5358.3333 | 10928.75 | 77047.6875 | 57556.8 | 7910 | 82.38% | 1092.875 | 7.05 | 5.71 | 10 | 10.93 | 70% | 75.18% | 1811811.55 | 2199224 | 27 | 24 | 3
JFL | 42687 | 1530868 | 1133796 | 397072 | 1360771.5556 | 226975.5556 | 109939.75 | 745391.505 | 253560.78 | 42188 | 73% | 9994.5227 | 6.78 | 5.94 | 11 | 10.21 | 74% | 68.68% | 6734748.24 | 9226031.1467 | 27 | 24 | 3
JKL | 97665 | 2684219 | 1935076 | 749143 | 2385972.4444 | 450896.4444 | 211702 | 1780413.82 | 753973.8 | 103312 | 74.45% | 21170.2 | 8.41 | 7.72 | 10 | 10.1 | 63% | 61.08% | 14938786.72 | 20066028.2578 | 27 | 24 | 3
MFL | 76383 | 2343006 | 1663098 | 679908 | 2082672 | 419574 | 189072.75 | 1395356.895 | 537736.32 | 84320 | 76.18% | 18907.275 | 7.38 | 7.04 | 10 | 8.75 | 71% | 67.01% | 11708209.92 | 15370119.36 | 27 | 24 | 3
FFL2 | 105301 | 3107863 | 2684752 | 423111 | 2762544.8889 | 77792.8889 | 132103 | 862632.59 | 654972.22 | 120818 | 92.57% | 13210.3 | 6.53 | 6.22 | 10 | 12.32 | 68% | 68.84% | 16699157.44 | 18039418.1244 | 27 | 24 | 3
JKL-U2 | 120328 | 4032281 | 3330223 | 702058 | 3584249.7778 | 254026.7778 | 205596.5 | 1624212.35 | 912086.24 | 131836 | 89.15% | 20559.65 | 7.9 | 7.58 | 10 | 10.36 | 68% | 68.36% | 25243090.34 | 28315573.2444 | 27 | 24 | 3
GTAL | 12365 | 0 | 745227 | -745227 | 0 | -745227 | -183215.5 | 0 | 58115.5 | 19243 | #DIV/0! | -18321.55 | 0 | 4.7 | 10 | 10.09 | 63% | 36.3% | 3502566.9 | 0 | 27 | 24 | 3
GMT TOTAL: | 553923 | 16773830 | 14043853 | 2729977 | 14910071.1111 | 866218.1111 | 820975 | 6058795.5 | 3592883.0587 | 596729 | 82.78% | 82097.5 | 7.38 | 6.4863 | 10 | 10.45 | 68.63% | 64.71% | 91091941.5212 | 110036324.8 | 27 | 24 | 3
LINGERIE | 125830 | 3336726 | 3134947 | 201779 | 2965978.6667 | -168968.3333 | 81902.25 | 343170.4275 | 483187.2 | 124942 | 96.87% | 8125.2232 | 4.19 | 3.84 | 10.08 | 10.3 | 79% | 74.28% | 12038196.48 | 12427450.6133 | 27 | 24 | 3
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
16773830 | 14043853 | 550000 | 1650000 | 15693853 | 1079977
- |  | 585000 | 1755000 | 15798853 | 974977
- |  | 620000 | 1860000 | 15903853 | 869977
- |  | 655000 | 1965000 | 16008853 | 764977
- |  | 690000 | 2070000 | 16113853 | 659977
- |  | 725000 | 2175000 | 16218853 | 554977